# Sunday Brunch With Giselle: Complete Production Plan

Your step-by-step roadmap from concept to thriving podcast community

## PHASE 1: FOUNDATION & PRE-PRODUCTION (Weeks 1-4)

### Week 1: Script Architecture & Character Voice Templates

#### Day 1-2: Episode Structure Template Creation

- Morning (2 hours): Create master episode timing template

  - Intro segment: Write 3 variations, time each, select best (target: 90 seconds)

  - "Before We Bake" segment: Draft opening ritual language (target: 2-3 minutes)

  - Story-to-recipe transition phrases: Write 10 bridge sentences for different moods

- Afternoon (1 hour): Map character segment timing

  - Giselle's Grand Verdicts: 90 seconds maximum

  - Havok's Kitchen Recon: 75 seconds maximum

  - Tiana's Tasting Notes: 60 seconds maximum

  - Phaedra's Porch Light: 90 seconds maximum

- Evening: Review and refine timing targets

#### Day 3-4: Character Voice Standardization

- Morning (2 hours): Giselle voice consistency

  - Write 20 different "royal decrees" in varying tones

  - Practice reading aloud, mark which feel most natural

  - Create "Giselle's vocabulary list" (her signature phrases)

- Afternoon (90 minutes): Havok's military voice

  - Draft 15 "mission report" openings

  - Time each delivery style, find optimal pace

  - Create his tactical jargon glossary

- Evening (90 minutes): Tiana & Phaedra consistency check

  - Write 10 enthusiastic Tiana responses to different foods

  - Draft 10 Phaedra philosophical observations

  - Test reading all characters back-to-back for voice distinctiveness

#### Day 5-7: Complete Episode Script #1 (French Silk Pie)

- Day 5 Morning (3 hours): Write complete intro through story segment

  - Full intro with natural Giselle interruptions

  - "Before We Bake" segment with sensory details

  - Personal story woven with recipe introduction

- Day 5 Afternoon (2 hours): Recipe walkthrough draft

  - Step-by-step with timing cues built in

  - Natural Giselle commentary points marked

  - Sensory descriptions for each major step

- Day 6 Morning (2 hours): All character segments

  - Write all four Sheltie segments for this episode

  - Time each segment with natural delivery

  - Ensure each serves the episode's emotional arc

- Day 6 Afternoon (1 hour): Outro and transitions

  - Smooth transitions between all segments

  - Compelling "next episode" tease

  - Warm, inclusive closing

- Day 7: Full read-through and timing

  - Record yourself reading entire script

  - Note pacing issues and awkward transitions

  - Revise for natural flow

### Week 2: Script Templates & Voice Refinement Completion

#### Day 8-10: Episode Script #2 (Different Recipe Type - Quick Bread)

- Day 8: Select recipe with different story potential (childhood memory vs. recent discovery)

- Follow same daily structure as Week 1, Days 5-7

- Focus: How does format adapt to simpler recipes with less dramatic backstory?

#### Day 11-12: Episode Script #3 (Cookie Recipe)

- Day 11: Choose recipe that allows for lighter, more whimsical storytelling

- Day 12: Complete script following established template

- Focus: Testing format flexibility for various emotional tones

#### Day 13-14: Template Refinement & Standardization

- Day 13 Morning: Compare all three scripts for consistency

  - Character voice consistency across episodes

  - Timing variations and optimal segment lengths

  - Transition phrases that work universally

- Day 13 Afternoon: Create master template document

  - Segment-by-segment template with timing goals

  - Character voice guidelines and phrase banks

  - Transition and bridge phrase library

- Day 14: Template testing

  - Use template to outline Episode #4 concept

  - Time how long it takes to create new episode using template

  - Adjust template based on efficiency and creative flow

### Week 3: Technical Setup & Recording Environment

#### Day 15-16: Recording Space Setup

- Day 15 Morning: Assess and optimize recording location

  - Test 3-4 different rooms for sound quality using phone voice recorder

  - Identify best corner/area within chosen room

  - Map out kitchen recording setup (where you'll record cooking segments)

- Day 15 Afternoon: Acoustic treatment (budget-friendly)

  - Hang blankets or towels to reduce echo

  - Test recording with makeshift acoustic treatment

  - Document optimal setup for consistency

- Day 16: Equipment setup and testing

  - Set up microphone and recording device/software

  - Test recording levels in both quiet room and kitchen

  - Record 5-minute test in your natural podcast voice

  - Adjust levels and positioning based on playback

#### Day 17-18: Recording Software Mastery

- Day 17 Morning (2 hours): Software tutorial deep-dive

  - Complete tutorial for chosen software (GarageBand, Audacity, or Descript)

  - Practice basic editing: cutting, fading, level adjustment

  - Learn how to create separate tracks for character voices

- Day 17 Afternoon: Practice editing workflow

  - Record 10-minute practice segment

  - Edit for optimal sound quality

  - Time your editing process for future planning

- Day 18: Advanced features exploration

  - Learn noise reduction and audio enhancement

  - Practice adding intro/outro music (royalty-free options)

  - Test exporting in proper podcast format

#### Day 19-21: ElevenLabs Voice Training for Giselle

- Day 19: ElevenLabs account setup and exploration

  - Create account and explore voice options

  - Test 5-6 different voices with Giselle's sample text

  - Note which voices best match your vision

- Day 20: Voice customization and training

  - If using voice cloning, record clean samples of desired tone

  - Test different settings for sass level, pace, and warmth

  - Create test segments using your Giselle voice templates

- Day 21: Integration testing

  - Practice workflow for recording your parts and adding Giselle

  - Test how Giselle's voice sits in the mix with yours

  - Adjust levels and pacing for natural conversation flow

### Week 4: Voice Development & Production Testing

#### Day 22-23: Personal Voice Development

- Day 22 Morning: Record your three completed scripts

  - Record Script #1 completely, focusing on natural delivery

  - Note sections where you sound stilted or rushed

  - Practice difficult transitions until they feel conversational

- Day 22 Afternoon: Playback analysis

  - Listen for filler words, pacing issues, energy drops

  - Mark sections that need re-recording

  - Note your natural rhythm and speech patterns

- Day 23: Voice coaching exercises

  - Practice varying your pace for different segment types

  - Work on smooth transitions between story and instruction

  - Record segment samples until each feels effortless

#### Day 24-25: Character Integration Practice

- Day 24: Giselle integration rehearsal

  - Record yourself having "conversations" with pre-recorded Giselle segments

  - Practice natural timing for her interruptions

  - Adjust your delivery to play well off her energy

- Day 25: Full cast integration

  - Practice introducing each character segment naturally

  - Work on your transitional phrases between character voices

  - Time complete character segment sequences

#### Day 26-28: Production Workflow Testing

- Day 26: Complete mini-episode production

  - Record 10-minute sample episode with all elements

  - Include intro, story segment, recipe portion, one character segment, outro

  - Add Giselle voice and basic editing

- Day 27: Editing and post-production

  - Complete full edit of mini-episode

  - Add music and sound effects

  - Time your complete production process

- Day 28: Workflow documentation and optimization

  - Document step-by-step production process

  - Identify bottlenecks and time-consuming steps

  - Create checklist for efficient weekly production

## PHASE 2: CONTENT STRATEGY & BLOG INTEGRATION (Weeks 5-8)

### Week 5: Recipe Portfolio Development

#### Day 29-31: Recipe Selection & Story Mapping

- Day 29 Morning: Brainstorm 25-30 potential recipes

  - List family recipes with rich stories

  - Include variety: cookies, pies, breads, cakes, bars

  - Note seasonal considerations for release timing

- Day 29 Afternoon: Story potential assessment

  - Rate each recipe for story richness (1-10)

  - Identify the core emotional theme for top 15 recipes

  - Map recipes to different character energy (some work better for Havok chaos, others for Phaedra wisdom)

- Day 30: Strategic recipe selection

  - Choose 12 recipes for first season (3 months of weekly episodes)

  - Ensure variety in difficulty, season, and story type

  - Consider visual appeal for blog integration

- Day 31: Detailed story development

  - Write 2-3 sentence story summary for each selected recipe

  - Identify the deeper theme (belonging, creativity, family, etc.)

  - Note which Sheltie characters each story naturally highlights

#### Day 32-35: Recipe Testing & Documentation

- Day 32-33: Test and photograph Recipe #1-3

  - Bake each recipe, noting timing and any adjustments

  - Take process photos for blog use

  - Write detailed notes about sensory experiences (sounds, smells, textures)

- Day 34-35: Test and document Recipe #4-6

  - Continue testing process

  - Begin creating standardized recipe cards

  - Note which steps naturally lend themselves to storytelling

### Week 6: Recipe Bridge Technique Development

#### Day 36-37: Bridge Technique Mastery

- Day 36 Morning: Analyze successful bridge examples

  - Study how cooking shows seamlessly blend story and instruction

  - Listen to narrative podcasts that incorporate "how-to" elements

  - Identify 5-7 different bridge techniques

- Day 36 Afternoon: Write bridge variations

  - Create 10 different ways to transition from story to recipe

  - Practice timing bridges with actual recipe steps

  - Test which feel most natural in your voice

- Day 37: Bridge technique application

  - Apply different bridge techniques to your 6 tested recipes

  - Record sample transitions to test effectiveness

  - Document which techniques work best for different story types

#### Day 38-42: Complete Recipe Development

- Day 38-40: Test remaining 6 recipes

  - Continue systematic testing and documentation

  - Focus on identifying the "magic moment" in each recipe (the step that's most transformative)

  - Create complete sensory notes for each

- Day 41-42: Recipe card standardization

  - Create consistent format for all 12 recipes

  - Include timing cues for podcast delivery

  - Add "story integration points" to each recipe card

### Week 7: Blog Foundation Setup

#### Day 43-44: Platform Selection & Setup

- Day 43: Research and choose blog platform

  - Compare WordPress, Squarespace, Wix for podcast integration

  - Consider ease of use, SEO capabilities, and audio embedding

  - Set up basic site structure

- Day 44: Design and branding consistency

  - Choose color palette and fonts that match podcast personality

  - Create logo/header incorporating Sheltie elements

  - Set up basic page structure (About, Recipes, Episodes, Contact)

#### Day 45-46: Content Structure Development

- Day 45: Blog post template creation

  - Design template that includes: episode embed, full recipe, story excerpt, photos

  - Create consistent formatting for recipe cards

  - Plan sidebar elements (recent episodes, popular recipes, Sheltie character bios)

- Day 46: SEO and discoverability setup

  - Research keywords for your niche (cozy baking, nostalgic recipes, etc.)

  - Set up basic SEO plugins and settings

  - Create category structure that supports both podcast and recipe discovery

#### Day 47-49: Blog Content Creation

- Day 47-48: Write blog posts for first 3 episodes

  - Create engaging post titles that work for both podcast and recipe audiences

  - Write compelling recipe descriptions that complement episode stories

  - Edit and optimize photos from recipe testing

- Day 49: Blog testing and optimization

  - Test user experience on both desktop and mobile

  - Ensure podcast episodes embed properly

  - Check page loading speeds and optimize if needed

### Week 8: Content Calendar & Social Media Strategy

#### Day 50-51: Content Calendar Development

- Day 50: Map 12-week content calendar

  - Schedule recipe releases considering seasonality

  - Plan special episodes (holidays, seasonal themes)

  - Identify opportunities for listener engagement (recipe submissions, Q&A)

- Day 51: Cross-platform content planning

  - Plan how each episode generates: blog post, social media content, email newsletter content

  - Create content batching schedule for efficient production

  - Plan seasonal content themes

#### Day 52-54: Social Media Strategy

- Day 52: Platform selection and setup

  - Set up Instagram, Pinterest, and one other platform (TikTok or Facebook)

  - Create consistent branding across platforms

  - Plan content types for each platform (process videos, finished photos, quotes, etc.)

- Day 53: Content template creation

  - Create 10 different social media post templates

  - Plan Story highlights structure (Recipes, Behind-the-scenes, Sheltie antics)

  - Design quote graphics template featuring character quotes

- Day 54: Social media content batch creation

  - Create 2 weeks worth of social content for launch

  - Practice efficient workflow for ongoing social media management

  - Set up scheduling tools if desired

#### Day 55-56: Email Marketing Setup

- Day 55: Newsletter platform setup

  - Choose and set up email marketing platform (Mailchimp, ConvertKit, etc.)

  - Create signup forms for blog and social media

  - Design welcome sequence for new subscribers

- Day 56: Email content planning

  - Plan weekly newsletter content (recipe of the week, behind-the-scenes, character spotlights)

  - Create newsletter template

  - Write first 4 newsletter issues

## PHASE 3: PILOT PRODUCTION (Weeks 9-12)

### Week 9: Pilot Episode #1 Production

#### Day 57-59: Pre-Production

- Day 57: Final script refinement for Episode #1

  - Polish script based on all learning from previous weeks

  - Time final script with stopwatch

  - Prepare all materials (ingredients, equipment, notes)

- Day 58: Recording prep day

  - Set up recording space optimally

  - Test all equipment and software

  - Do vocal warm-ups and practice key transitions

- Day 59: Kitchen prep and setup

  - Pre-measure ingredients for smooth recording

  - Set up kitchen recording station

  - Test recording quality in kitchen vs. main recording space

#### Day 60-63: Recording & Initial Edit

- Day 60: Record main content

  - Record intro, story, and recipe segments

  - Allow extra time for natural delivery

  - Record multiple takes of challenging sections

- Day 61: Record character segments

  - Generate Giselle segments using ElevenLabs

  - Record all other character segments

  - Ensure consistent audio levels across all segments

- Day 62-63: Complete first edit

  - Assemble complete episode

  - Add intro/outro music

  - Balance all audio levels

  - Export first complete episode

### Week 10: Pilot Episode #2 & #3 Production

#### Day 64-67: Episode #2 Production

- Days 64-66: Follow same production schedule as Episode #1

- Day 67: Focus on workflow efficiency

  - Time each production step

  - Note improvements in process

  - Document any technical issues and solutions

#### Day 68-70: Episode #3 Production

- Days 68-70: Streamlined production using lessons learned

- Focus on consistency in audio quality and timing

- Test different character segment orders

### Week 11: Post-Production Polish

#### Day 71-73: Advanced Editing & Sound Design

- Day 71: Episode #1 final polish

  - Add subtle sound effects (kitchen sounds, etc.)

  - Fine-tune character segment transitions

  - Create final master file

- Day 72-73: Episodes #2 & #3 final polish

  - Apply same advanced editing techniques

  - Ensure consistency across all three episodes

  - Create episode artwork for each

#### Day 74-77: Quality Control & Testing

- Day 74: Audio quality analysis

  - Listen to all three episodes on different devices (headphones, car speakers, phone)

  - Check for consistent volume levels

  - Note any audio issues for correction

- Day 75: Content review

  - Review each episode for pacing and engagement

  - Ensure character voices remain consistent

  - Verify recipe instructions are clear and complete

- Day 76-77: Episode description and metadata

  - Write compelling episode descriptions

  - Create timestamps for different segments

  - Prepare all metadata for podcast hosting platform

### Week 12: Test & Feedback Integration

#### Day 78-80: Beta Testing

- Day 78: Select beta listeners

  - Choose 5-7 people from target demographic

  - Include both friends and some objective listeners if possible

  - Provide listening instructions and feedback forms

- Day 79-80: Distribute pilot episodes

  - Send episodes with specific questions for feedback

  - Ask about pacing, character likability, recipe clarity

  - Request honest feedback on overall engagement

#### Day 81-84: Feedback Integration

- Day 81-82: Analyze feedback

  - Compile all feedback into categories (content, pacing, characters, technical)

  - Identify consistent themes in feedback

  - Prioritize changes based on impact and feasibility

- Day 83-84: Implement key improvements

  - Make necessary adjustments to format or delivery

  - Re-record sections if needed

  - Update templates and processes based on learnings

  - Finalize pilot episodes for potential launch use

## PHASE 4: LAUNCH STRATEGY (Weeks 13-16)

### Week 13: Pre-Launch Foundation

#### Day 85-87: Podcast Hosting Setup

- Day 85: Choose and set up podcast host

  - Research platforms (Anchor, Buzzsprout, Libsyn) for features and pricing

  - Set up account and upload pilot episodes

  - Configure RSS feed and basic settings

- Day 86: Podcast directory submission prep

  - Create podcast artwork (3000x3000 pixels minimum)

  - Write compelling podcast description

  - Prepare category selections and tags

- Day 87: Submit to major directories

  - Submit to Apple Podcasts, Spotify, Google Podcasts

  - Submit to additional directories (Stitcher, Amazon Music, etc.)

  - Set up podcast website integration

#### Day 88-91: Marketing Foundation

- Day 88-89: Create launch announcement content

  - Design announcement graphics for all social platforms

  - Write launch announcement blog post

  - Create email announcement for newsletter

- Day 90-91: Influencer and community outreach prep

  - Research similar podcasts and bloggers in cozy/baking niches

  - Prepare personalized outreach messages

  - Create media kit with show information and assets

### Week 14: Community Building & Partnerships

#### Day 92-94: Strategic Partnerships

- Day 92: Reach out to complementary creators

  - Contact baking bloggers for potential recipe exchanges

  - Reach out to cozy lifestyle podcasters for cross-promotion

  - Connect with pet/dog content creators for Sheltie angle

- Day 93-94: Community engagement setup

  - Create Facebook group or Discord for listeners

  - Set up engagement strategies for social media

  - Plan interactive content (polls, recipe requests, etc.)

#### Day 95-98: Pre-Launch Buzz Creation

- Day 95-96: Behind-the-scenes content creation

  - Create "making of" content for social media

  - Share Sheltie "audition" videos or photos

  - Post kitchen setup and recording space glimpses

- Day 97-98: Teaser content rollout

  - Share audio clips from pilot episodes

  - Post recipe photos with "coming soon" messaging

  - Create anticipation with countdown posts

### Week 15: Launch Week

#### Day 99-101: Soft Launch

- Day 99: Release Episode #1

  - Publish first episode early morning

  - Share across all social media platforms

  - Send newsletter announcement

  - Engage actively with any early listeners

- Day 100-101: Monitor and engage

  - Respond to all comments and messages

  - Share listener posts/stories

  - Post additional behind-the-scenes content

#### Day 102-105: Full Launch Push

- Day 102: Release Episode #2

  - Follow same promotion strategy as Episode #1

  - Begin weekly release schedule

  - Monitor download numbers and engagement

- Day 103-105: Amplification efforts

  - Share episodes in relevant Facebook groups (with permission)

  - Engage with podcast communities

  - Continue outreach to potential collaborators

### Week 16: Launch Optimization & Future Planning

#### Day 106-108: Analytics Review & Optimization

- Day 106: Analyze first week metrics

  - Review download numbers, completion rates, geographic data

  - Check social media engagement and website traffic

  - Identify which promotion methods were most effective

- Day 107-108: Content optimization

  - Adjust future episode planning based on audience response

  - Optimize social media strategy based on engagement

  - Plan improvements to website and blog based on traffic patterns

#### Day 109-112: Sustainable Growth Strategy

- Day 109-110: Long-term content planning

  - Plan next 8-10 episodes based on launch learnings

  - Schedule seasonal content and special episodes

  - Plan listener engagement initiatives (recipe contests, Q&A episodes)

- Day 111-112: Systems optimization

  - Streamline production workflow based on experience

  - Set up sustainable schedule for ongoing content creation

  - Plan growth strategies and potential monetization options

## SUCCESS METRICS TO TRACK THROUGHOUT

### Week 1-4 Metrics:

- Script completion times

- Character voice consistency ratings (self-assessed)

- Recording setup quality tests

- Template usability and efficiency

### Week 5-8 Metrics:

- Recipe testing success rates

- Blog setup completion milestones

- Content creation efficiency improvements

- Social media engagement on teaser content

### Week 9-12 Metrics:

- Production time per episode

- Beta listener feedback scores

- Audio quality consistency

- Content engagement predictions

### Week 13-16 Metrics:

- Podcast directory approval rates

- Download numbers and growth trends

- Social media follower growth

- Website traffic and blog engagement

- Email subscriber growth

- Listener retention rates (completion percentages)

## WEEKLY TIME INVESTMENT GUIDE

Weeks 1-4: 15-20 hours/week (heavy foundational work) Weeks 5-8: 12-15 hours/week (content creation and setup) Weeks 9-12: 10-12 hours/week (production learning curve) Weeks 13-16: 8-10 hours/week (launch activities) Ongoing: 6-8 hours/week (sustainable production schedule)

Remember: This timeline is ambitious but achievable. If any week feels overwhelming, extend it by a few days rather than rushing. Quality and sustainability matter more than speed. Your cozy kitchen empire is worth building thoughtfully!